## Sep-2026
Timesheet — Arnav Johri ¦ Associate Consultant (SAP ABAP) ¦ Diligent Global
Client: KPMG ¦ Period: 01-Sep-2026 to 30-Sep-2026
Date | Day | Client | Object / WRICEF | Task Description | Hours | Status
2026-09-01 | Tue | KPMG | ZMM_VEND_UPLOAD | Analysed BP/vendor master fields for upload template | 1 | Completed
2026-09-01 | Tue | KPMG | ZPP_FORECAST | Unit testing of annual/quarterly/monthly forecast save | 3 | Completed
2026-09-01 | Tue | KPMG | General | Transport request organisation and documentation of changes | 2.5 | Completed
2026-09-01 | Tue | KPMG | ZSD_SCHEME | Reviewed open queries on scheme application with SD functional | 1.5 | Completed
2026-09-02 | Wed | KPMG | ZPP_FORECAST | Reviewed CR on forecast refinements with functional; queries raised before build | 3.5 | Completed
2026-09-02 | Wed | KPMG | ZPP_FORECAST_UPLOAD | Resolved activation errors in upload program | 1.5 | Completed
2026-09-02 | Wed | KPMG | ZPP_FORECAST_UPLOAD | Added overall result message after upload | 3 | Completed
2026-09-03 | Thu | KPMG | ZPP_FORECAST | Built CR: month split, price columns and old-material tracking | 3.5 | Completed
2026-09-03 | Thu | KPMG | ZPP_FORECAST | Quarterly ALV regrouped month-wise with headings from fiscal calendar | 4.5 | Completed
2026-09-04 | Fri | KPMG | ZSD_EXC_APPROVAL | Packaged exceptional approval objects (141A/B) for abapGit upload | 3.5 | Completed
2026-09-04 | Fri | KPMG | ZSD_EXC_APPROVAL | Prepared upload steps document for exceptional approval objects | 4.5 | Completed
2026-09-07 | Mon | KPMG | ZFI_TDS_CL34 | Added F4 help for section code and vendor code (with ALPHA conversion) | 4 | Completed
2026-09-07 | Mon | KPMG | ZFI_TDS_CL34 | Excluded non-reportable withholding tax item statuses in data selection | 1 | Completed
2026-09-07 | Mon | KPMG | ZFI_TDS_CL34 | Added Debit/Credit indicator column; report title updated as per Clause 34(a) | 2 | Completed
2026-09-07 | Mon | KPMG | ZPP_FORECAST | Supported QAS initial testing setup for forecast application | 1 | Completed
2026-09-08 | Tue | Leave | - | On leave | 0 | Leave
2026-09-09 | Wed | Leave | - | On leave | 0 | Leave
2026-09-10 | Thu | Leave | - | On leave | 0 | Leave
2026-09-11 | Fri | Leave | - | On leave | 0 | Leave
2026-09-14 | Mon | KPMG | ZFI_TDS_CL34 | Discussed report observations with FI functional | 2 | Completed
2026-09-14 | Mon | KPMG | General | Daily status call with KPMG team; updated issue tracker | 4 | Completed
2026-09-14 | Mon | KPMG | ZPP_FORECAST | Analysed tester observations on forecast report and replied with findings | 2 | Completed
2026-09-15 | Tue | KPMG | ZPP_FORECAST | Price derivation from condition records, value columns and material type restriction | 4 | Completed
2026-09-15 | Tue | KPMG | ZPP_FORECAST | Monthly history read from billing data, aligned with quarterly logic | 4 | Completed
2026-09-16 | Wed | KPMG | General | Transport request organisation and documentation of changes | 4 | Completed
2026-09-16 | Wed | KPMG | ZMM_VEND_UPLOAD | Reviewed FSD for vendor upload program; clarifications raised | 4 | Completed
2026-09-17 | Thu | KPMG | ZPP_FORECAST | Supported functional testing of forecast application in QAS | 1.5 | Completed
2026-09-17 | Thu | KPMG | ZMM_VEND_UPLOAD | Reviewed FSD for vendor upload program; clarifications raised | 3 | Completed
2026-09-17 | Thu | KPMG | General | Daily status call with KPMG team; updated issue tracker | 3.5 | Completed
2026-09-18 | Fri | KPMG | ZPP_FORECAST_UPLOAD | Fixed legacy history upload storing month values in wrong columns | 2.5 | Completed
2026-09-18 | Fri | KPMG | ZPP_FORECAST_UPLOAD | Unit tested history upload with single-month and full-year files | 1 | Completed
2026-09-18 | Fri | KPMG | ZFI_TDS_CL34 | Discussed report observations with FI functional | 1.5 | Completed
2026-09-18 | Fri | KPMG | ZSD_EXC_APPROVAL | Supported testing of exceptional approval formats (Adhesives/Paints) | 3 | Completed
2026-09-21 | Mon | KPMG | ZSD_MIS_CUSTOMER | Reviewed FS for WRICEF 147 (CC MIS summary, customer-wise) | 2 | Completed
2026-09-21 | Mon | KPMG | ZSD_MIS_CUSTOMER | Prepared feasibility assessment and query list for functional | 2 | Completed
2026-09-21 | Mon | KPMG | ZSD_EXC_APPROVAL | Supported testing of exceptional approval formats (Adhesives/Paints) | 1.5 | Completed
2026-09-21 | Mon | KPMG | ZPP_FORECAST | Unit testing of annual/quarterly/monthly forecast save | 2.5 | Completed
2026-09-22 | Tue | KPMG | ZPP_FORECAST | Analysed tester observations on forecast report and replied with findings | 2 | Completed
2026-09-22 | Tue | KPMG | ZMM_BP_CREATE_MAIL | FS 057 walkthrough and design discussion | 2 | Completed
2026-09-22 | Tue | KPMG | General | Transport request organisation and documentation of changes | 4 | Completed
2026-09-23 | Wed | KPMG | ZPP_FORECAST | Superseded material on selection screen now shown under its successor | 3.5 | Completed
2026-09-23 | Wed | KPMG | ZPP_FORECAST | Added MSL to monthly business forecast: upload, storage, display and total | 4.5 | Completed
2026-09-24 | Thu | KPMG | ZSD_EXC_APPROVAL | Supported testing of exceptional approval formats (Adhesives/Paints) | 4 | Completed
2026-09-24 | Thu | KPMG | ZPP_FORECAST | Analysed tester observations on forecast report and replied with findings | 4 | Completed
2026-09-25 | Fri | KPMG | ZMM_BP_CREATE_MAIL | Developed supplier BP creation mail program from FS 057 | 4 | Completed
2026-09-25 | Fri | KPMG | ZMM_BP_CREATE_MAIL | Fixed ALV column text dump and column widths | 4 | Completed
2026-09-28 | Mon | KPMG | ZSD_EXC_APPROVAL | Supported testing of exceptional approval formats (Adhesives/Paints) | 2.5 | Completed
2026-09-28 | Mon | KPMG | ZFI_TDS_CL34 | Discussed report observations with FI functional | 2.5 | Completed
2026-09-28 | Mon | KPMG | ZMM_BP_CREATE_MAIL | FS 057 walkthrough and design discussion | 1.5 | Completed
2026-09-28 | Mon | KPMG | ZSD_SCHEME | Reviewed open queries on scheme application with SD functional | 1.5 | Completed
2026-09-29 | Tue | KPMG | ZFI_TDS_CL34 | Prepared TS document (WRICEF 337) in client template | 3 | Completed
2026-09-29 | Tue | KPMG | ZFI_TDS_CL34 | Reviewed report output with functional for TS sign-off | 2 | Completed
2026-09-29 | Tue | KPMG | ZPP_FORECAST | Analysed tester observations on forecast report and replied with findings | 1.5 | Completed
2026-09-29 | Tue | KPMG | General | Daily status call with KPMG team; updated issue tracker | 1.5 | Completed
2026-09-30 | Wed | KPMG | ZPP_FORECAST | Old material codes' history filled from legacy sales table where billing missing | 3 | Completed
2026-09-30 | Wed | KPMG | ZPP_FORECAST | Validated forecast figures against tester's data in DEV | 1.5 | Completed
2026-09-30 | Wed | KPMG | ZFI_FB70_CM_APPRV | Designed FB70 credit memo approval workflow; skeleton build sheet | 3.5 | Completed
Total hours
|  |  |  | Working days | 18
|  |  |  | Leave days (08–11 Sep) | 4